## Sheet1
Project Timetable | Start Date | End Date | Completed
Review code sent by Professor of the sample module | 2017-06-08 | 2017-06-15
Develop module to transmit text to search engine. Develop in Python | 2017-06-15 | 2017-06-27
Work on SMTP module with Divya | 2017-06-28 | ---
Next Steps?
Work on sms via twilio code
integrate to project
verify number in china
a small python script to import java code
everything gets displayed in one big gui
take a list of rss feeds search for keywords - ‘china’, ‘chinese’
run per frequency inverse document frequency
identifying and anylzing documents and finding most common keywords
cluster